## Feuil1
Gantt chart
| April |  |  | May |  |  |  |  | June
| Week 1 | Week 2 | Week 3 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
literature review | bar: April Week 1 to April Week 2; May Week 6
system developpement | bar: April Week 2 to May Week 4; May Week 6 to May Week 7
data preprocessing | bar: May Week 4 to May Week 5
algorithm development | bar: May Week 6 to June Week 8
testing | bar: June Week 9 to June Week 11
evaluation
report writing
| July |  |  |  |  | August
| Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 16 | Week 17
literature review
system developpement
data preprocessing
algorithm development
testing
evaluation | bar: July Week 12 to July Week 13
report writing | bar: July Week 14 to July Week 15